## Sheet1
Gantt Chart of 489 Project
	Trimester 1
Activities	~150 Hours @ ~10hrs per week	151 Hours @ ~10hrs per week	152 Hours @ ~10hrs per week	153 Hours @ ~10hrs per week	154 Hours @ ~10hrs per week	155 Hours @ ~10hrs per week	156 Hours @ ~10hrs per week	157 Hours @ ~10hrs per week	158 Hours @ ~10hrs per week	159 Hours @ ~10hrs per week	160 Hours @ ~10hrs per week	161 Hours @ ~10hrs per week	162 Hours @ ~10hrs per week	163 Hours @ ~10hrs per week
Create 489 proposal	5 hrs
Produce summaries/bibliography of research documents	30 hrs	16 hrs	17 hrs	18 hrs
Produce feasibility study of existing technologies		10 hrs
Decide on chosen solution and produce initial plans				15 hrs	11 hrs
Conduct implementation of solution					90 hrs
Milestone Report					10 hrs
	18/03	25/03	01/04	08/04	15/04	22/04	29/04	06/05	13/05	20/05	27/05	03/06	10/06	17/06	24/06

	Mid year break
Conduct implementation of solution
Produce follow up design/technology considerations
1 Week Buffer Zone for catch up
	01/07	08/07

	Trimester 2
Activities	~150 Hours @ ~10hrs per week
Conduct evaluation and produce report	40hrs
Produce final report and prepare presentation					60hrs
	15/07	22/07	29/07	05/08	12/08	19/08	26/08	02/09	09/09	16/09	23/09	30/09	07/10	14/10	18/10